## Overall schedule
Note: the Reporting & Insights team uses the word 'feature' to refer to what Azure Devops calls a Product Backlog Item
| Friday & Monday |  |  | Tuesday |  | Wednesday |  | Thursday |  | Friday
| Old Sprint's Last Days |  |  | Sprint Transition |  | Sprint Transition |  | Sprint Transition |  | New Sprint Starts
Time | Meeting? | Meeting Description | To-do | Meeting? | To-do | Meeting? | To-do | Meeting? | To-do | Meeting? | To-do
start of work day-10am |  |  | Prepare for meeting • Demonstration of any shareable progress and atomic metrics accessibility • For each feature you own, determine worked-on status (delivered, partial, or zero)and whether to move to the next feature or attempt to finish in the sprint transition. • If feature is incomplete, explain why. • Identify if you have any vacation days in the current sprint |  | • decompose tasks (both your own tasks and coworkers' tasks under your features and look for tasks that can be removed) • identify lingers for sprint planning • Complete commits from old sprint, if any |  | • decompose tasks (both your own tasks and coworkers' tasks under your features and look for tasks that can be removed) • identify lingers for sprint planning • Complete commits from old sprint, if any |  | Plan committed features for next sprint |  | work
10am-10:30am/11am | SCRUM | normal SCRUM but also mentioning which features may extend into the Sprint transition |  | The 3 Monday meetings may be moved to Tuesday |  |  |  | SCRUM | normal SCRUM but also mentioning which features have been completed in the Sprint transition | No meetings | work
| Sprint Review | Riad updates the statuses of features in Azure DevOps | review prior sprint features and share demonstrations |  | Communicate with coworkers about changing feature priorities and checking status of tasks to be finished in prior sprint |  | Communicate with coworkers about changing feature priorities and checking status of tasks to be finished in prior sprint | (The Wednesday SCRUM may be moved to Thursday) | Verbalize if any leftover features from the Old Sprint have been completed |  | work
| Sprint Planning A | move features into the current sprint for potential decomp. Moving extra features is ok | assign features to the New sprint and prioritize them |  |  |  |  | Sprint Commit | Identify committed features for next sprint |  | work
11am-end of work day |  |  | decompose tasks |  | • decompose tasks (both your own tasks and coworkers' tasks under your features and look for tasks that can be removed) • identify lingers for sprint planning • Complete commits from old sprint, if any |  | • decompose tasks (both your own tasks and coworkers' tasks under your features and look for tasks that can be removed) • identify lingers for sprint planning • Complete commits from old sprint, if any |  |  |  | work